## Sheet1
Capstone Schedule
Week | Date (Fri) | Mile Stones | Session date (Sat/ Sun) | Session Plan
Week-0 | 24th April 2020 | Start of capstone. | NA | No session
Release the Capstone problem statement & Grouping
Week-1 | 1st May 2020 | Release Interim Report | 2nd/3rd May | Discussion of Problem Statement, Delegation of responsibilities among team members, Planning the progress and approach to capstone
Group discussion on the respective problem statement released
Week-2 | 8th May 2020 | Milestone-1: EDA and Pre-processing (Feature engineering and selection | 9th/10th May | Review progress of team & individuals contributions, Pointing out errors, suggesting alternative methods, clarification of conceptual roadblocks if any.
Week-3 | 15th May 2020 | Milestone-1: Modelling (Focus on accuracy and generalization) & interim Report Submission | 16th/17th May | Validate the interim submission and suggest improvements if any. Raise alarms for proactive correction
|  | Release Final Report |  | Interim report submission - 17th May 2020
Week-4 | 22nd May 2020 |  | 23rd/24th May
|  | Milestone-2: Evaluation of your model (Comparison of different models, performance tuning) |  | Review the progress towards final reporting
Week-5 | 29th May 2020 | Milestone-2: Final model tuning and documentation | 30th/31st May | Validation of the final report and suggestions of correction before submission
Week-6 | 5th June 2020 | Milestone-2: Presentation to the mentor | 06th/07th June | Presentation of capstone project by students to mentor
|  | Final Report submission on Olympus |  | 7th June 2020- Final Report Submission